## Sheet1
** Add Club name here **
Annual General Meeting - ** add year here **
Meeting Date: | 2024-11-23
Task | Constitution Timeline | Date Due | Person Responsible | Date Completed
Retiring Committee renomination letters due | Prior to AGM notice distribution | 2024-10-13
Send out notification of meeting to members and call for committee nominations | Minimum 40 days prior to meeting | 2024-10-14
Prepare nomination packs for members | Minimum 40 days prior to meeting | 2024-10-14
Member nominations for Management Committee due to Club | 14 days following notification of meeting | 2024-10-28
Voting papers distributed (only if new nominations are received) | 7 days following nomination closing date | 2024-11-04
Due date for new business to be mentioned at meeting | 14 days prior to meeting | 2024-11-09
Voting closing date | 14 days following dissemination of voting papers | 2024-11-18
Annual Report/Audited Financials distributed to members | 14 days prior to meeting | 2024-11-09
Voting paper distribution list:
Letter with nominees
Voting instructions
Biographies
Last AGM minutes
Annual report
2 x envelopes
Formulas:
Date Due = [Date Due, row below]-1
Date Due = [Date Due, row above]+7